## Sheet1
SUBJECTS COVERED TRAINING MODULES | PLANNING / STRATEGIC PROGRAMMING | BASICS OF PROGRAMMING | ADVANCED PROGRAMMING | NEC PROGRAMMING
Planning
Choice of programme method - linked bar chart (GANTT), line of balance etc. | YES |  | YES
Preparation of tender price & cost breakdown structure (CBS) | YES |  | YES
JCT - BoQ's / Sched of Works / Sched of rates | YES |  | YES
NEC - Sched of Cost Components / Activity Schedule | YES |  | YES | YES
Identification of resources - organisation breakdown structure (OBS) | YES |  | YES
Defining the Work Breakdown Structure (WBS) | YES |  | YES
Developing the tender price CBS & OBS into the programme WBS | YES |  | YES | YES
Choosing the right contract / subcontract forms | YES |  | YES | YES
Defining subcontractors programming requirements | YES |  | YES | YES
Contingency planning vs float - project contingency, weather, planned vs contract completion dates | YES |  | YES | YES
Programming
Calendars |  | YES | YES | YES
Working time |  | YES |  | YES
Non-working time |  | YES |  | YES
5 day or 7 day? |  | YES |  | YES
Dealing with different calendars in the same programme |  | OVERVIEW ONLY | YES | OVERVIEW ONLY
Outline Structure
What is the outline structure - levels, hiding and showing levels for reporting | YES | YES | YES | YES
Defining the outline structure - tender level | YES | YES | YES | YES
Defining the outline structure - contract programme | YES | YES | YES | YES
Overview of outline structure v coding v sort order |  | YES | YES | YES
Defining the outline structure including CBS, OBS, WBS |  | YES | YES | YES
Entering Tasks
Indicative tasks for tender programme |  | YES | OVERVIEW ONLY | OVERVIEW ONLY
Discrete tasks for contract programme |  | YES | OVERVIEW ONLY | OVERVIEW ONLY
Effect of task durations - definition of work, calendar days, elapsed days |  | YES | OVERVIEW ONLY | OVERVIEW ONLY
Tasks by 'Others' |  | YES | OVERVIEW ONLY | OVERVIEW ONLY
Definition and use of milestones |  | YES | OVERVIEW ONLY | OVERVIEW ONLY
Start date, possession date, completion date, planned completion date |  | YES | OVERVIEW ONLY | OVERVIEW ONLY
Constraints - why they should only be of limited use |  | YES | OVERVIEW ONLY | OVERVIEW ONLY
Linking Tasks
Definition of links - FS, SS, FF, SF - and which not to use and why |  | YES | YES | YES
Defintion of lead / lag times |  | YES | YES | YES
When to use lead/lag and when to use a task |  | YES | YES | YES
Discussion of mid task links, uses and problems |  | OVERVIEW ONLY | YES | YES
Definition of ladders and problems with ladders |  | OVERVIEW ONLY | YES | YES
Grouping / outlining of tasks - how to avoid too many links |  | OVERVIEW ONLY | YES | YES
Float
Definitions of free and total float - early & late start & finish | YES | YES | YES | YES
Definition of critical paths |  | YES | YES | YES
Networks - an overview of what sits behind the programme software & how the critical path is calculated |  | YES | YES | YES
Application of float within different forms of contract - JCT / NEC | YES | YES | YES | YES
Use of float vs contingency planning | YES | YES | YES | YES
Dealing with float and progress - effects on planned start dates | YES | YES | YES | YES
Negative float |  |  | YES
Checking the Programme
Hints and tips for checking - too many links, link gradient, float evaluation |  | YES | YES | YES
Compliance with NEC clause 31.2 |  |  |  | YES
Progress reporting and Rescheduling
Calculating the critical path(s) | YES | OVERVIEW ONLY | YES | YES
Progress entry | YES | OVERVIEW ONLY | YES | YES
Jagged line progress reporting | YES | OVERVIEW ONLY | YES | YES
Rescheduling and calculation of a revised planned completion date | YES | OVERVIEW ONLY | YES | YES
Reporting issues - contract completion or revised planned completion and the role of task float | YES |  | YES | YES
Compliance with NEC clause 32.1 |  |  |  | YES
Advanced sorting & coding
Coding the programme | YES |  | YES
Subcontractor / trades programmes | YES |  | YES
Building area coding | YES |  | YES
Sorting the programme - e.g. walk order sorting | YES |  | YES
Resources
Application of resources to the programme to produce an overview histogram |  |  | YES
Costing
Application of costs to the programme to produce an overview S curve |  |  | YES
Delay Analysis
Application of delays / VO's / CE's to the programme |  |  | YES | YES
Retrospective / prospective / combined analysis |  |  | YES | YES
Establishing entitlement to EoT / additional time |  |  | YES | YES
Multiple delays |  |  | YES | YES
Definitions of concurrency |  |  | YES | YES
The legal position regarding concurrency |  |  | YES | YES
NEC dealing with ongoing multiple CE's |  |  |  | YES
Other Issues
Tables and views |  |  | YES
Baselines and versions |  |  | YES
Multiple progress in one programme or multiple programmes | YES |  | YES